## Gantt Chart Template
Gantt Chart Template
Project Name: Mobile Banking Application
| Task Name | Start (Date) | End (Date) | Duration (Days)
| Gather Data | 2024-03-01 | 2024-03-03 | 2
| Create Charts | 2024-03-03 | 2024-03-04 | 1
| Create Plan | 2024-03-04 | 2024-03-06 | 2
| Schedule Work | 2024-03-06 | 2024-03-08 | 2
| Bank account creation module | 2024-03-10 | 2024-03-28 | 18
| Credit card module | 2024-03-10 | 2024-03-28 | 18
| Send money to another account module | 2024-03-10 | 2024-03-28 | 18
| Send money between own accounts module | 2024-03-10 | 2024-03-28 | 18
| Seeing the history of transactions module | 2024-03-10 | 2024-03-28 | 18
| Project Completion | 2024-03-28 | 2024-03-31 | 3

## How To Use This Template
Introduction
Use this template to help you plan projects! When you update columns B, C, & D in the other tab your gantt chart will automatically update.