## TRACK MY TASKS
Task Tracking Template
Project Name Here
Task Name/ Description | Dependent Tasks | Assigned To | Priority | Start Date | Planned End Date | Actual End Date | Status | Notes
Research for project | Create project plan | Mariyan Apostolov | Medium | 2024-03-01 | 2024-03-03 | 29/2/2024 | CLOSED
Create project plan | 01. Creating a bank account 02. Creation of credit card 03. Send money to another account 04. Send money between own accounts 05. Seeing the history of transactions | Mariyan Apostolov | High | 2024-03-03 | 2024-03-08 | 2024-03-02 | CLOSED
01. Creating a bank account | Project Completion | Mariyan Apostolov | Medium | 2024-03-08 | 2024-03-29 | 2024-03-25 | CLOSED
02. Creation of credit card | Project Completion | Mariyan Apostolov | Medium | 2024-03-08 | 2024-03-29 | 2024-03-28 | CLOSED
03. Send money to another account | Project Completion | Mariyan Apostolov | Medium | 2024-03-08 | 2024-03-29 | 2024-03-27 | CLOSED
04. Send money between own accounts | Project Completion | Mariyan Apostolov | Medium | 2024-03-08 | 2024-03-29 | 2024-03-27 | CLOSED
05. Seeing the history of transactions | Project Completion | Mariyan Apostolov | Medium | 2024-03-08 | 2024-03-29 | 2024-03-28 | CLOSED
Project Complation |  | Mariyan Apostolov | High | 2024-03-29 | 2024-04-01 | 2024-03-29 | CLOSED
To add another row to your list, click the "insert" button in the top right, and then click "insert table row below."

## How to Use this Template
Introduction
Use this template to track your tasks. As a team member, or a manager, it's critical to take care of your daily work so the team can remain productive as a whole. Of course, you can use this template to track your tasks at home too!
Definition of Terms
MY TASKS: Enter the name of the task you need to do.
ASSIGNED TO: Enter the name of the person responsible for this task
PRIORITY: Enter low, medium, high, or critical
START DATE: Enter the date you need to start the task.
PLANNED END DATE: this is the intended due date
ACTUAL END DATE: Enter the date the task actually finished
Notes: Add any notes for context that you need.
To add another row to your list, click the "insert" button in the top right, and then click "insert table row below"